## Project Planner
Snake-like Robot
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 42 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) |  |  | % Complete (beyond plan)
LEAD | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
ALL | Documentation | 40 | 10 | 40 |  | 10%
RUBEN | Modeling | 40 | 3 | 40 |  | 70%
MARCUS/RUBEN | Printing | 41 | 2 | 41 |  | 50%
MARCUS | Assembly | 42 | 1 | 42 |  | 50%
HÅKON | Movement Code | 42 | 2 | 42 |  | 80%
MARCUS | Image Processing | 43 | 4 | 42 |  | 1.667%
| Maze | 43 | 3 | 42 |  | 5%
| Find snake | 46 | 1 |  |  | 0%
| Find target | 46 | 1 |  |  | 0%
RUBEN/HÅKON | Comm PC/ESP32 | 42 | 1 | 42 |  | 90%
MARCUS/HÅKON | Integrate ImPro/Movement | 45 | 3 |  |  | 0%
| Send commands | 45 | 1 |  |  | 0%
| Collision detect | 46 | 1 |  |  | 0%
| See the maze | 47 | 1 |  |  | 0%
Håkon | Pathfinding | 44 | 4 |  |  | 10%
| Integrate maze | 44 | 2 |  |  | 0%
| Optimization | 46 | 2 |  |  | 0%
| Algorithm | 43 | 1 | 43 |  | 30%
| Remote | 43 | 2 |  |  | 0%
| Build GUI | 43 | 1 |  |  | 0%
| Controlling | 43 | 1 |  |  | 0%
| Monitoring | 44 | 1 |  |  | 0%
Ruben | Logging | 45 | 1 | 43 |  | 40%
ALL | Testing | 47 | 2 |  |  | 0%